## Sheet1
Milestone | Task | Status | Estimated Time | Goal Date | Dependence | Comments | File Links | Key:
Planning and Set-Up | Create Teams Group | Completed | 5 min | 2021-10-22 |  | Use teams for chat and outside meetings |  | Luke
| Elevator Pitch | Completed | 45 min | 2021-10-25 |  |  | Elevator Pitch | Daniel
| Rough Outline | Completed | 1 hour | 2021-10-26 | Elevator Pitch |  | Rough Outline | Elwood
| Make Git Repository | Completed | 15 min | 2021-10-28 |  |  | Github Repository | Douglas
| Find Data Sources | Completed | 1 hour | 2021-10-26 | Rough Outline |  | Data Sources | Group
| Exploratory Questions | Completed | 30 min | 2021-10-28 |  |  | Exploratory Questions
| Create Project Specifications Documents | Completed | 2 Hours | 2021-10-29 |  |  | Project Specifications
ETL | Create Data Lake Container | Completed | 5 min | 2021-10-27 |  |  | Data Lake Container
| Select Indicators | Completed | 1 hour | 2021-10-27 | Exploratory Questions |  | World Bank Indicators
| Create Country Code List | Completed | 1 hour | 2021-10-27
| API Call Function | Completed | 1 hour | 2021-10-27
| Formatting Messages for Producer | Completed | 1 hour | 2021-10-27 | API Call Function
| Receiving Messages with Consumer | Completed | 1 hour | 2021-10-27 | Formatting Messages for Producer
| Save to CSV | Completed | 30 min | 2021-10-27 | Receiving Messages with Consumer
| Save to SQL | Completed | 30 min | 2021-10-27 | Receiving Messages with Consumer
| Create Data Factory | Completed | 10 min | 2021-10-27 | Producer/Consumer Creation
| Connect Data Factory to Databricks | Completed | 10 min | 2021-10-27
| Write ETL Report | Completed | 2 hours | 2021-11-01 | Completion of ETL, may require revision
| Create Cloud Server Diagram | Completed | 30 min | 2021-10-28 | Completion of ETL |  | Data Flow Diagram
Machine Learning | Process and Standardize Data | Completed | 1 Hour | 2021-11-01 | Save to SQL
| Choose a Machine Learning Model | Completed | 1 Hour | 2021-11-03
| Test, Train, and HyperTune Model | Completed | 2 Hours | 2021-11-04 | Process and Standardize Data | If we run into roadblocks this step could take a lot longer. Give an adequate time cushion to account for any roadblocks.
| Interpret Results | Completed | 1 Hour | 2021-11-05 | Test, Train, and HyperTune Model | Figure out what final recommendations should be
| Export Model for Outside Use | Completed | 30 min | 2021-11-05 | Test, Train, and HyperTune Model
Dashboard | Select Dashboard Service | Completed | 10 min | 2021-11-08 |  | Will be using Power BI
| Create Napkin Drawings for Visualizations; Get Feedback | Completed | 1 Hour | 2021-11-08 |  | Split up the drawings evenly
| Create Napkin Drawings for Dashboard; Get Feedback | Completed | 1 Hour | 2021-11-08 |  | Split up the drawings evenly
| Import Data from SQL with ML | Completed | 1 Hour | 2021-11-08 | Save to SQL
| Create Visualizations | Completed | 2 Hours | 2021-11-08 | Import Data from SQL with ML | Split up the visualizations evenly
| Fine Tune Layout, Text, and Colors | Completed | 1 Hour | 2021-11-08 | Create Visualizations | All group members will agree on final dashboard
Report | Write Introduction | Completed | 30 min | 2021-11-08
| Present and Explain Research | Completed | 2 hours | 2021-11-08
| Summarize Project Steps | Completed | 1.5 hours | 2021-11-08
| Write Conclusion | Completed | 15 min | 2021-11-08
| Review, Revise, and Finalize Report | Started | 1 hour | 2021-11-10
Presentation | Introduction Slides | Started | 30 min | 2021-11-10 | Completion of Report
| Question Slides | Started | 30 min | 2021-11-10 | Completion of Report
| Research Slides | Started | 1 hour | 2021-11-10 | Completion of Report
| Machine Learning Slides | Started | 1.5 hours | 2021-11-10 | Completion of Report
| Recommendation Slides | Started | 30 min | 2021-11-10 | Completion of Report
| Presentation Dry Run | Started | 1 hour | 2021-11-11 | Completion of Presentation